## Project Info
PROJECT GANTT CHART TEMPLATE
Project Info › Tasks › Gantt › Holidays – everything is linked; fill the yellow cells only
PROJECT DETAILS |  | SCHEDULE HEALTH (auto-calculated)
Project Name | Website Redesign & Launch | Planned Finish (baseline) | 2026-12-17
Client Name | Acme Corporation | Forecast Finish (incl. delays) | 2026-12-31
Project Manager | Your Name | Target Completion Date | 2026-12-18
Project Code / Reference | PRJ-2026-001 | Delay vs TARGET (working days) | 8
Project Start Date | 2026-10-05 | Delay vs PLAN (working days) | 9
Target Completion Date | 2026-12-18 | Overall % Complete (duration weighted) | 39.32%
Status (Report) Date | 2026-11-06 | Calendar days late vs Target | 13
Weekly Off | Saturday & Sunday |  |  |  | 1
Gantt View (set on Gantt sheet) | Week
⚠ PROJECT DELAYED: forecast finish 31-Dec-2026 is 8 working day(s) after target 18-Dec-2026
STATUS BY COMPONENT (tasks whose name starts with the text in column B)
Component (name prefix) | Planned Finish | Forecast Finish | Delay vs Plan (wd) | % Complete
DESIGN | 2026-11-09 | 2026-11-23 | 9 | 62.07%
BUILD | 2026-11-24 | 2026-12-07 | 9 | 44.86%
LAUNCH | 2026-12-17 | 2026-12-31 | 9 | 0%
TASK STATISTICS |  | HOW TO USE
Total Tasks | 14 | 1. Fill the yellow Project Details: start / target / report date and the Weekly Off.
Completed | 4 | 2. Holidays sheet: list non-working dates.
In Progress | 3 | 3. Tasks sheet: Task Name + Duration (working days) + predecessor ID(s). Link FS = after predecessor ends (default); SS = starts n days after it starts; FF = ends n days after it ends. Lag in working days.
Not Started / On Hold | 7 | 4. Update progress: Status, Actual Start/End, % Complete. Use Revised Duration when you expect an overshoot.
Tasks Overshooting Duration | 3 | 5. Gantt sheet: pick Day / Week / Month in cell B2; scroll the timeline with C2.
Tasks Affected by Others' Delay | 10 | 6. 300 task rows are pre-built; copy the last row down to add more.
Largest Overshoot (task) | DESIGN ¦ UX wireframes (+7 d) | 7. Avoid circular links (A waits for B and B waits for A).
Total Planned Task-Days | 88 | Yellow cells = input · white cells = formulas (do not overwrite).
COLOUR LEGEND
Completed | Task finished (bar portion within planned duration)
In Progress | Task started, not finished
Not Started | Scheduled, not yet begun
On Hold | Task paused
Overshoot | Time used beyond the planned DURATION (task ran / is expected to run over)
Delayed / Affected | Start pushed out by a late predecessor or by the status date (see 'Impact' column)
Planned (not used) | Planned time no longer used (finished early / started late)
Weekly off | Weekly-off day (Day view)
Holiday | Dates from the Holidays sheet (pink header in Week/Month view = holiday inside period)
Status Date | Column of the report date set above
▶ Start | First day of a task with no predecessor
↳ Dependent start | First day of a task that waits for a predecessor
◀ End | Last day of a task
➜ End feeds others | Last day of a task that other tasks depend on
◆ Start = End | Task starts and ends in the same period
Formulas:
Planned Finish = IF(OR([Component (name prefix)]="",COUNTIF(Tasks!$B11:B310,[Component (name prefix)]&"*")=0),"",SUMPRODUCT(MAX((LEFT(Tasks!$B11:B310,LEN([Component (name prefix)]))=[Component (name prefix)])*Tasks!$AI11:AI310)))
Forecast Finish = IF(OR([Component (name prefix)]="",COUNTIF(Tasks!$B11:B310,[Component (name prefix)]&"*")=0),"",SUMPRODUCT(MAX((LEFT(Tasks!$B11:B310,LEN([Component (name prefix)]))=[Component (name prefix)])*Tasks!$AJ11:AJ310)))
Delay vs Plan (wd) = IF(OR([Planned Finish]="",[Forecast Finish]=""),"",IF([Forecast Finish]>=[Planned Finish],NETWORKDAYS.INTL([Planned Finish],[Forecast Finish],'Project Info'!$H12,Holidays!$A6:A205)-1,-(NETWORKDAYS.INTL([Forecast Finish],[Planned Finish],'Project Info'!$H12,Holidays!$A6:A205)-1)))
Note on C9: Project execution start (EXEC: date of techno-commercially clear PO + advance).
Note on C11: Date up to which progress is reported. =TODAY() tracks live. Un-started tasks cannot start before this date; in-progress tasks are measured against it.

## Tasks
TASK LIST – Website Redesign & Launch ¦ Client: Acme Corporation
Type in the YELLOW cells only. Link: FS = starts after predecessor ends (blank = FS) · SS = starts n days after it starts · FF = ends n days after it ends. Lag / duration are WORKING days (weekly-off & holidays skipped).
⚠ PROJECT DELAYED: forecast finish 31-Dec-2026 is 8 working day(s) after target 18-Dec-2026
Planned finish: 17-Dec-26 ¦ Forecast finish: 31-Dec-26 ¦ Target: 18-Dec-26 ¦ Overall progress: 39% ¦ Status date: 06-Nov-26
① TASK ENTRY | [10 empty] | ② STATUS UPDATE |  |  |  |  | ③ SCHEDULE & ANALYSIS (automatic) | [9 empty] | helper
ID | Task Name | Owner | Pred. 1 (ID) | Link 1 (FS/SS/FF) | Lag 1 (days) | Pred. 2 (ID) | Link 2 (FS/SS/FF) | Lag 2 (days) | Duration (work days) | Start No Earlier Than (optional) | Status | Actual Start | Actual End | % Complete | Revised Duration (if overshoot) | Planned Start | Planned End | Forecast / Actual Start | Forecast / Actual End | Forecast / Actual Duration | Duration Variance (days) | Duration Status | End Slip vs Plan (days) | Impact (affected by) | No. of Dependent Links | class | has pred | pred1 slip | pred2 slip | eff status | eff % | end if no overshoot | weighted done | planned end (num) | fcst end (num)
1 | DESIGN ¦ Project kickoff & charter | Project Manager | [6 empty] | 2 |  | Completed | 2026-10-05 | 2026-10-06 | 100% |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | 2 | 0 | Completed - On Time | 0 |  | 1 | 1 | 0 | 0 | 0 | Completed | 100% | 2026-10-06 | 2 | 46301 | 46301
2 | DESIGN ¦ Requirements gathering | Business Analyst | 1 | FS | 0 |  |  |  | 5 |  | Completed | 2026-10-07 | 2026-10-15 | 100% |  | 2026-10-07 | 2026-10-13 | 2026-10-07 | 2026-10-15 | 7 | 2 | Completed - Overshoot | 2 |  | 3 | 1 | 1 | 0 | 0 | Completed | 100% | 2026-10-13 | 5 | 46308 | 46310
3 | DESIGN ¦ Technical architecture | Architect | 2 | FS | 0 |  |  |  | 4 |  | Completed | 2026-10-16 | 2026-10-21 | 100% |  | 2026-10-14 | 2026-10-19 | 2026-10-16 | 2026-10-21 | 3 | -1 | Completed - Early | 1 | Delayed by Task #2 (+2d) | 1 | 1 | 1 | 2 | 0 | Completed | 100% | 2026-10-22 | 4 | 46314 | 46316
4 | DESIGN ¦ UX wireframes | UX Designer | 2 | FS | 0 |  |  |  | 10 |  | In Progress | 2026-10-16 |  | 70% | 17 | 2026-10-14 | 2026-10-28 | 2026-10-16 | 2026-11-11 | 17 | 7 | In Progress - Overshooting | 9 | Delayed by Task #2 (+2d) | 1 | 2 | 1 | 2 | 0 | In Progress | 70% | 2026-10-30 | 7 | 46323 | 46337
5 | DESIGN ¦ Visual design | UI Designer | 4 | FS | 0 |  |  |  | 8 |  | Not Started |  |  |  |  | 2026-10-29 | 2026-11-09 | 2026-11-12 | 2026-11-23 | 8 | 0 | Delayed Start | 9 | Delayed by Task #4 (+9d) | 1 | 7 | 1 | 9 | 0 | Not Started | 0% | 2026-11-23 | 0 | 46335 | 46349
6 | BUILD ¦ Database setup | DBA | 3 | FS | 0 |  |  |  | 5 |  | Completed | 2026-10-22 | 2026-10-30 | 100% |  | 2026-10-21 | 2026-10-27 | 2026-10-22 | 2026-10-30 | 7 | 2 | Completed - Overshoot | 3 | Delayed by Task #3 (+1d) | 2 | 1 | 1 | 1 | 0 | Completed | 100% | 2026-10-28 | 5 | 46322 | 46325
7 | BUILD ¦ Backend API development | Dev Team A | 6 | FS | 0 |  |  |  | 12 |  | In Progress | 2026-11-02 |  | 30% |  | 2026-10-28 | 2026-11-13 | 2026-11-02 | 2026-11-18 | 12 | 0 | In Progress - On Track | 3 | Delayed by Task #6 (+3d) | 1 | 2 | 1 | 3 | 0 | In Progress | 30% | 2026-11-18 | 3.6 | 46339 | 46344
8 | BUILD ¦ Frontend development | Dev Team B | 5 | FS | 0 | 6 | FS | 0 | 10 |  | Not Started |  |  |  |  | 2026-11-11 | 2026-11-24 | 2026-11-24 | 2026-12-07 | 10 | 0 | Delayed Start | 9 | Delayed by Task #5 (+9d) | 1 | 7 | 1 | 9 | 3 | Not Started | 0% | 2026-12-07 | 0 | 46350 | 46363
9 | BUILD ¦ Content creation | Content Lead | 2 | FS | 0 |  |  |  | 10 | 2026-10-26 | In Progress | 2026-10-26 |  | 80% |  | 2026-10-26 | 2026-11-06 | 2026-10-26 | 2026-11-06 | 10 | 0 | In Progress - On Track | 0 |  | 1 | 2 | 1 | 2 | 0 | In Progress | 80% | 2026-11-06 | 8 | 46332 | 46332
10 | LAUNCH ¦ Integration & QA testing | QA Team | 7 | FS | 0 | 8 | FS | 0 | 8 |  | Not Started |  |  |  |  | 2026-11-25 | 2026-12-04 | 2026-12-08 | 2026-12-17 | 8 | 0 | Delayed Start | 9 | Delayed by Task #8 (+9d) | 1 | 7 | 1 | 3 | 9 | Not Started | 0% | 2026-12-17 | 0 | 46360 | 46373
11 | LAUNCH ¦ User acceptance testing | Client | 10 | FS | 0 |  |  |  | 5 |  | Not Started |  |  |  |  | 2026-12-07 | 2026-12-11 | 2026-12-18 | 2026-12-24 | 5 | 0 | Delayed Start | 9 | Delayed by Task #10 (+9d) | 1 | 7 | 1 | 9 | 0 | Not Started | 0% | 2026-12-24 | 0 | 46367 | 46380
12 | LAUNCH ¦ Training & documentation | Trainer | 9 | FS | 0 |  |  |  | 5 |  | On Hold |  |  |  |  | 2026-11-09 | 2026-11-16 | 2026-11-09 | 2026-11-16 | 5 | 0 | On Hold | 0 |  | 1 | 4 | 1 | 0 | 0 | On Hold | 0% | 2026-11-16 | 0 | 46342 | 46342
13 | LAUNCH ¦ Deployment / go-live | DevOps | 11 | FS | 0 | 12 | FS | 0 | 2 |  | Not Started |  |  |  |  | 2026-12-14 | 2026-12-15 | 2026-12-28 | 2026-12-29 | 2 | 0 | Delayed Start | 9 | Delayed by Task #11 (+9d) | 1 | 7 | 1 | 9 | 0 | Not Started | 0% | 2026-12-29 | 0 | 46371 | 46385
14 | LAUNCH ¦ Project closure & handover | Project Manager | 13 | FS | 0 |  |  |  | 2 |  | Not Started |  |  |  |  | 2026-12-16 | 2026-12-17 | 2026-12-30 | 2026-12-31 | 2 | 0 | Delayed Start | 9 | Delayed by Task #13 (+9d) | 0 | 7 | 1 | 9 | 0 | Not Started | 0% | 2026-12-31 | 0 | 46373 | 46387
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
Formulas:
Planned End = IF(OR([Planned Start]="",NOT(ISNUMBER([Duration (work days)]))),"",WORKDAY.INTL([Planned Start],MAX(1,[Duration (work days)])-1,'Project Info'!$H12,Holidays!$A6:A205))
Forecast / Actual End = IF(OR([Forecast / Actual Start]="",[Forecast / Actual Duration]=""),"",IF(ISNUMBER([Actual End]),[Actual End],WORKDAY.INTL([Forecast / Actual Start],[Forecast / Actual Duration]-1,'Project Info'!$H12,Holidays!$A6:A205)))
End Slip vs Plan (days) = IF(OR(NOT(ISNUMBER([Planned End])),NOT(ISNUMBER([Forecast / Actual End]))),"",IF([Forecast / Actual End]>=[Planned End],NETWORKDAYS.INTL([Planned End],[Forecast / Actual End],'Project Info'!$H12,Holidays!$A6:A205)-1,-(NETWORKDAYS.INTL([Forecast / Actual End],[Planned End],'Project Info'!$H12,Holidays!$A6:A205)-1)))
end if no overshoot = IF(OR([Forecast / Actual Start]="",NOT(ISNUMBER([Duration (work days)]))),"",WORKDAY.INTL([Forecast / Actual Start],MAX(1,[Duration (work days)])-1,'Project Info'!$H12,Holidays!$A6:A205))

## Gantt
GANTT ¦ Website Redesign & Launch ¦ Acme Corporation | [13 empty] | ⚠ PROJECT DELAYED: forecast finish 31-Dec-2026 is 8 working day(s) after target 18-Dec-2026
| Week | 0 |  | ◀ pick Day / Week / Month · Scroll = shift timeline by n periods (+ later / − earlier)
LEGEND ▸ bar colour = task status · RED part of a bar = time over the planned duration | [13 empty] | Completed | [7 empty] | In Progress | [7 empty] | Not Started | [7 empty] | On Hold | [7 empty] | Overshoot (over duration) | [7 empty] | Delayed / Affected | [7 empty] | Planned, unused
Orange task name = delayed by predecessor · Red task name = duration overshoot · Pink header = holiday | [13 empty] | Weekly off | [7 empty] | Holiday | [7 empty] | Status date | [7 empty] | ▶ Start | [7 empty] | ↳ Starts after pred. | [7 empty] | ◀ End | [7 empty] | ➜ End feeds others | [7 empty] | ◆ Start = End
2026-10-05 | time axis 2026-10-05 to 2029-01-15
 | time axis 2026-10-11 to 2029-01-21
[14 empty] | 0 | 0 | 3 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TASK SCHEDULE (Plan vs Forecast / Actual) | [13 empty] | 2026-10-11: Oct 26; 2026-11-08: Nov 26; 2026-12-13: Dec 26; 2027-01-10: Jan 27; 2027-02-07: Feb 27; 2027-03-07: Mar 27; 2027-04-11: Apr 27; 2027-05-09: May 27; 2027-06-13: Jun 27; 2027-07-11: Jul 27; 2027-08-08: Aug 27; 2027-09-12: Sep 27; 2027-10-10: Oct 27; 2027-11-07: Nov 27; 2027-12-12: Dec 27; 2028-01-09: Jan 28; 2028-02-13: Feb 28; 2028-03-12: Mar 28; 2028-04-09: Apr 28; 2028-05-07: May 28; 2028-06-11: Jun 28; 2028-07-09: Jul 28; 2028-08-13: Aug 28; 2028-09-10: Sep 28; 2028-10-08: Oct 28; 2028-11-12: Nov 28; 2028-12-10: Dec 28; 2029-01-07: Jan 29
[14 empty] | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W01 | W02 | W03
ID | Task | Depends On | Plan Start | Plan End | Fcst / Actual Start | Fcst / Actual End | Status | % Done | Var (days) |  |  |  |  | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15
1 | DESIGN ¦ Project kickoff & charter | - | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Completed | 100% | 0 | 1 | 0 | 1 | 46301 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | DESIGN ¦ Requirements gathering | 1 | 2026-10-07 | 2026-10-13 | 2026-10-07 | 2026-10-15 | Completed | 100% | 2 | 1 | 1 | 3 | 46308 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | DESIGN ¦ Technical architecture | 2 | 2026-10-14 | 2026-10-19 | 2026-10-16 | 2026-10-21 | Completed | 100% | -1 | 1 | 1 | 1 | 46317 | 0 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DESIGN ¦ UX wireframes | 2 | 2026-10-14 | 2026-10-28 | 2026-10-16 | 2026-11-11 | In Progress | 70% | 7 | 2 | 1 | 1 | 46325 | 0 | 22 | 20 | 20 | 50 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | DESIGN ¦ Visual design | 4 | 2026-10-29 | 2026-11-09 | 2026-11-12 | 2026-11-23 | Not Started | 0% | 0 | 7 | 1 | 1 | 46349 | 0 | 0 | 0 | 60 | 60 | 72 | 70 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BUILD ¦ Database setup | 3 | 2026-10-21 | 2026-10-27 | 2026-10-22 | 2026-10-30 | Completed | 100% | 2 | 1 | 1 | 2 | 46323 | 0 | 0 | 12 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUILD ¦ Backend API development | 6 | 2026-10-28 | 2026-11-13 | 2026-11-02 | 2026-11-18 | In Progress | 30% | 0 | 2 | 1 | 1 | 46344 | 0 | 0 | 0 | 60 | 22 | 20 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | BUILD ¦ Frontend development | 5, 6 | 2026-11-11 | 2026-11-24 | 2026-11-24 | 2026-12-07 | Not Started | 0% | 0 | 7 | 1 | 1 | 46363 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 72 | 70 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | BUILD ¦ Content creation | 2 | 2026-10-26 | 2026-11-06 | 2026-10-26 | 2026-11-06 | In Progress | 80% | 0 | 2 | 1 | 1 | 46332 | 0 | 0 | 0 | 22 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | LAUNCH ¦ Integration & QA testing | 7, 8 | 2026-11-25 | 2026-12-04 | 2026-12-08 | 2026-12-17 | Not Started | 0% | 0 | 7 | 1 | 1 | 46373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 72 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | LAUNCH ¦ User acceptance testing | 10 | 2026-12-07 | 2026-12-11 | 2026-12-18 | 2026-12-24 | Not Started | 0% | 0 | 7 | 1 | 1 | 46380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 72 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | LAUNCH ¦ Training & documentation | 9 | 2026-11-09 | 2026-11-16 | 2026-11-09 | 2026-11-16 | On Hold | 0% | 0 | 4 | 1 | 1 | 46342 | 0 | 0 | 0 | 0 | 0 | 42 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | LAUNCH ¦ Deployment / go-live | 11, 12 | 2026-12-14 | 2026-12-15 | 2026-12-28 | 2026-12-29 | Not Started | 0% | 0 | 7 | 1 | 1 | 46385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | LAUNCH ¦ Project closure & handover | 13 | 2026-12-16 | 2026-12-17 | 2026-12-30 | 2026-12-31 | Not Started | 0% | 0 | 7 | 1 | 0 | 46387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Holidays
HOLIDAY LIST
Enter one non-working date per row (yellow cells). Weekly off day(s) are set on the Project Info sheet. Holidays move task dates and are shaded pink on the Gantt chart.
Holiday Date | Holiday Name | Day
2026-10-20 | Sample holiday 1 (edit me) | Tuesday
2026-11-10 | Sample holiday 2 (edit me) | Tuesday
2026-12-25 | Christmas Day | Friday