## Project Info
PROJECT EXECUTION – GANTT CHART
Project Info › Tasks › Gantt › Holidays – everything is linked; fill the yellow cells only
PROJECT DETAILS |  | SCHEDULE HEALTH (auto-calculated)
Project Name | 1.8M C-Band Antenna System – 500 Sets | Planned Finish (baseline) | 2027-04-23
Client Name | <Client name> | Forecast Finish (incl. delays) | 2027-04-23
Project Manager | <Project manager> | Target Completion Date | 2027-04-23
Project Code / Reference | PRJ-2026-001 | Delay vs TARGET (working days) | 0
Project Start Date | 2026-10-15 | Delay vs PLAN (working days) | 0
Target Completion Date | 2027-04-23 | Overall % Complete (duration weighted) | 0%
Status (Report) Date | 2026-10-08 | Calendar days late vs Target | 0
Weekly Off | Sunday only |  |  |  | 11
Gantt View (set on Gantt sheet) | Week
✔ ON TRACK: forecast finish 23-Apr-2027 meets target 23-Apr-2027
STATUS BY COMPONENT (tasks whose name starts with the text in column B)
Component (name prefix) | Planned Finish | Forecast Finish | Delay vs Plan (wd) | % Complete
REFLECTOR | 2027-03-04 | 2027-03-04 | 0 | 0%
FEED | 2027-04-23 | 2027-04-23 | 0 | 0%
METAL | 2027-01-16 | 2027-01-16 | 0 | 0%
TASK STATISTICS |  | HOW TO USE
Total Tasks | 30 | 1. Fill the yellow Project Details: start / target / report date and the Weekly Off.
Completed | 0 | 2. Holidays sheet: list non-working dates.
In Progress | 0 | 3. Tasks sheet: Task Name + Duration (working days) + predecessor ID(s). Link FS = after predecessor ends (default); SS = starts n days after it starts; FF = ends n days after it ends. Lag in working days.
Not Started / On Hold | 30 | 4. Update progress: Status, Actual Start/End, % Complete. Use Revised Duration when you expect an overshoot.
Tasks Overshooting Duration | 0 | 5. Gantt sheet: pick Day / Week / Month in cell B2; scroll the timeline with C2.
Tasks Affected by Others' Delay | 0 | 6. 300 task rows are pre-built; copy the last row down to add more.
Largest Overshoot (task) | None | 7. Avoid circular links (A waits for B and B waits for A).
Total Planned Task-Days | 432 | Yellow cells = input · white cells = formulas (do not overwrite).
COLOUR LEGEND
Completed | Task finished (bar portion within planned duration)
In Progress | Task started, not finished
Not Started | Scheduled, not yet begun
On Hold | Task paused
Overshoot | Time used beyond the planned DURATION (task ran / is expected to run over)
Delayed / Affected | Start pushed out by a late predecessor or by the status date (see 'Impact' column)
Planned (not used) | Planned time no longer used (finished early / started late)
Weekly off | Weekly-off day (Day view)
Holiday | Dates from the Holidays sheet (pink header in Week/Month view = holiday inside period)
Status Date | Column of the report date set above
▶ Start | First day of a task with no predecessor
↳ Dependent start | First day of a task that waits for a predecessor
◀ End | Last day of a task
➜ End feeds others | Last day of a task that other tasks depend on
◆ Start = End | Task starts and ends in the same period
Formulas:
Planned Finish = IF(OR([Component (name prefix)]="",COUNTIF(Tasks!$B11:B310,[Component (name prefix)]&"*")=0),"",SUMPRODUCT(MAX((LEFT(Tasks!$B11:B310,LEN([Component (name prefix)]))=[Component (name prefix)])*Tasks!$AI11:AI310)))
Forecast Finish = IF(OR([Component (name prefix)]="",COUNTIF(Tasks!$B11:B310,[Component (name prefix)]&"*")=0),"",SUMPRODUCT(MAX((LEFT(Tasks!$B11:B310,LEN([Component (name prefix)]))=[Component (name prefix)])*Tasks!$AJ11:AJ310)))
Delay vs Plan (wd) = IF(OR([Planned Finish]="",[Forecast Finish]=""),"",IF([Forecast Finish]>=[Planned Finish],NETWORKDAYS.INTL([Planned Finish],[Forecast Finish],'Project Info'!$H12,Holidays!$A6:A205)-1,-(NETWORKDAYS.INTL([Forecast Finish],[Planned Finish],'Project Info'!$H12,Holidays!$A6:A205)-1)))
Note on C9: Project execution start (EXEC: date of techno-commercially clear PO + advance).
Note on C11: Date up to which progress is reported. =TODAY() tracks live. Un-started tasks cannot start before this date; in-progress tasks are measured against it.

## Tasks
TASK LIST – 1.8M C-Band Antenna System – 500 Sets ¦ Client: <Client name>
Type in the YELLOW cells only. Link: FS = starts after predecessor ends (blank = FS) · SS = starts n days after it starts · FF = ends n days after it ends. Lag / duration are WORKING days (weekly-off & holidays skipped).
✔ ON TRACK: forecast finish 23-Apr-2027 meets target 23-Apr-2027
Planned finish: 23-Apr-27 ¦ Forecast finish: 23-Apr-27 ¦ Target: 23-Apr-27 ¦ Overall progress: 0% ¦ Status date: 08-Oct-26
① TASK ENTRY | [10 empty] | ② STATUS UPDATE |  |  |  |  | ③ SCHEDULE & ANALYSIS (automatic) | [9 empty] | helper
ID | Task Name | Owner | Pred. 1 (ID) | Link 1 (FS/SS/FF) | Lag 1 (days) | Pred. 2 (ID) | Link 2 (FS/SS/FF) | Lag 2 (days) | Duration (work days) | Start No Earlier Than (optional) | Status | Actual Start | Actual End | % Complete | Revised Duration (if overshoot) | Planned Start | Planned End | Forecast / Actual Start | Forecast / Actual End | Forecast / Actual Duration | Duration Variance (days) | Duration Status | End Slip vs Plan (days) | Impact (affected by) | No. of Dependent Links | class | has pred | pred1 slip | pred2 slip | eff status | eff % | end if no overshoot | weighted done | planned end (num) | fcst end (num)
1 | REFLECTOR ¦ Finalize 1.8M mold design | Design | [6 empty] | 7 |  | Not Started |  |  |  |  | 2026-10-15 | 2026-10-23 | 2026-10-15 | 2026-10-23 | 7 | 0 | Not Started | 0 |  | 1 | 3 | 0 | 0 | 0 | Not Started | 0% | 2026-10-23 | 0 | 46318 | 46318
2 | REFLECTOR ¦ Mold manufacturing | Tooling | 1 | FS | 0 |  |  |  | 70 |  | Not Started |  |  |  |  | 2026-10-24 | 2027-01-19 | 2026-10-24 | 2027-01-19 | 70 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-19 | 0 | 46406 | 46406
3 | REFLECTOR ¦ Reflector validation | QA | 2 | FS | 0 |  |  |  | 7 |  | Not Started |  |  |  |  | 2027-01-20 | 2027-01-27 | 2027-01-20 | 2027-01-27 | 7 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-27 | 0 | 46414 | 46414
4 | REFLECTOR ¦ Production (500 nos @ 35/day) | Production | 3 | FS | 0 |  |  |  | 15 |  | Not Started |  |  |  |  | 2027-01-28 | 2027-02-13 | 2027-01-28 | 2027-02-13 | 15 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-02-13 | 0 | 46431 | 46431
5 | REFLECTOR ¦ Finishing & packing (35/day) | Finishing | 4 | FS | 0 |  |  |  | 15 |  | Not Started |  |  |  |  | 2027-02-15 | 2027-03-03 | 2027-02-15 | 2027-03-03 | 15 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-03-03 | 0 | 46449 | 46449
6 | REFLECTOR ¦ Dispatch – 8 vehicles (rolling) | Logistics | 5 | SS | 2 | 5 | FF | 1 | 14 |  | Not Started |  |  |  |  | 2027-02-17 | 2027-03-04 | 2027-02-17 | 2027-03-04 | 14 | 0 | Not Started | 0 |  | 0 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-03-04 | 0 | 46450 | 46450
7 | FEED ¦ Finalize mold design (6 components) | Design | [6 empty] | 15 |  | Not Started |  |  |  |  | 2026-10-15 | 2026-11-02 | 2026-10-15 | 2026-11-02 | 15 | 0 | Not Started | 0 |  | 1 | 3 | 0 | 0 | 0 | Not Started | 0% | 2026-11-02 | 0 | 46328 | 46328
8 | FEED ¦ Mold making – Round 1 (Horn, Splitter, Tx Filter) | Tooling | 7 | FS | 0 |  |  |  | 30 |  | Not Started |  |  |  |  | 2026-11-03 | 2026-12-11 | 2026-11-03 | 2026-12-11 | 30 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2026-12-11 | 0 | 46367 | 46367
9 | FEED ¦ Mold making – Round 2 (Rx Filter, Tx/Rx OMT) | Tooling | 8 | FS | 0 |  |  |  | 30 |  | Not Started |  |  |  |  | 2026-12-12 | 2027-01-16 | 2026-12-12 | 2027-01-16 | 30 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-16 | 0 | 46403 | 46403
10 | FEED ¦ Molding – Round-1 components (1,500 nos) | Molding | 8 | FS | 0 |  |  |  | 4 |  | Not Started |  |  |  |  | 2026-12-12 | 2026-12-16 | 2026-12-12 | 2026-12-16 | 4 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2026-12-16 | 0 | 46372 | 46372
11 | FEED ¦ Molding – Round-2 components (1,500 nos) | Molding | 9 | FS | 0 | 10 | FS | 0 | 4 |  | Not Started |  |  |  |  | 2027-01-18 | 2027-01-21 | 2027-01-18 | 2027-01-21 | 4 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-21 | 0 | 46408 | 46408
12 | FEED ¦ Machining – Round 1, Batch 1 (750 nos) | Machining | 10 | FS | 0 |  |  |  | 15 |  | Not Started |  |  |  |  | 2026-12-17 | 2027-01-04 | 2026-12-17 | 2027-01-04 | 15 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-04 | 0 | 46391 | 46391
13 | FEED ¦ Machining – Round 1, Batch 2 (750 nos) | Machining | 12 | FS | 0 |  |  |  | 15 |  | Not Started |  |  |  |  | 2027-01-05 | 2027-01-21 | 2027-01-05 | 2027-01-21 | 15 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-21 | 0 | 46408 | 46408
14 | FEED ¦ Machining – Round 2, Batch 1 (750 nos) | Machining | 11 | FS | 0 | 13 | FS | 0 | 15 |  | Not Started |  |  |  |  | 2027-01-22 | 2027-02-08 | 2027-01-22 | 2027-02-08 | 15 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-02-08 | 0 | 46426 | 46426
15 | FEED ¦ Machining – Round 2, Batch 2 (750 nos) | Machining | 14 | FS | 0 |  |  |  | 15 |  | Not Started |  |  |  |  | 2027-02-09 | 2027-02-25 | 2027-02-09 | 2027-02-25 | 15 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-02-25 | 0 | 46443 | 46443
16 | FEED ¦ Transport Batch 1 (250 sets) to finishing site | Logistics | 14 | FS | 0 |  |  |  | 1 |  | Not Started |  |  |  |  | 2027-02-09 | 2027-02-09 | 2027-02-09 | 2027-02-09 | 1 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-02-09 | 0 | 46427 | 46427
17 | FEED ¦ Finishing – Batch 1 (1,500 components) | Finishing | 16 | FS | 0 |  |  |  | 25 |  | Not Started |  |  |  |  | 2027-02-10 | 2027-03-10 | 2027-02-10 | 2027-03-10 | 25 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-03-10 | 0 | 46456 | 46456
18 | FEED ¦ Assembly & testing – Batch 1 (250 sets) | Assembly & QA | 17 | FS | 0 |  |  |  | 9 |  | Not Started |  |  |  |  | 2027-03-11 | 2027-03-20 | 2027-03-11 | 2027-03-20 | 9 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-03-20 | 0 | 46466 | 46466
19 | FEED ¦ Packing – Batch 1 (100/day) | Packing | 18 | FS | 0 |  |  |  | 3 |  | Not Started |  |  |  |  | 2027-03-22 | 2027-03-24 | 2027-03-22 | 2027-03-24 | 3 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-03-24 | 0 | 46470 | 46470
20 | FEED ¦ Dispatch – Vehicle 1 (150 sets) | Logistics | 19 | SS | 2 |  |  |  | 1 |  | Not Started |  |  |  |  | 2027-03-24 | 2027-03-24 | 2027-03-24 | 2027-03-24 | 1 | 0 | Not Started | 0 |  | 0 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-03-24 | 0 | 46470 | 46470
21 | FEED ¦ Transport Batch 2 (250 sets) | Logistics | 15 | FS | 0 |  |  |  | 1 |  | Not Started |  |  |  |  | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 1 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-02-26 | 0 | 46444 | 46444
22 | FEED ¦ Finishing – Batch 2 (1,500 components) | Finishing | 21 | FS | 0 | 17 | FS | 0 | 25 |  | Not Started |  |  |  |  | 2027-03-11 | 2027-04-08 | 2027-03-11 | 2027-04-08 | 25 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-04-08 | 0 | 46485 | 46485
23 | FEED ¦ Assembly & testing – Batch 2 (250 sets) | Assembly & QA | 22 | FS | 0 | 18 | FS | 0 | 9 |  | Not Started |  |  |  |  | 2027-04-09 | 2027-04-19 | 2027-04-09 | 2027-04-19 | 9 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-04-19 | 0 | 46496 | 46496
24 | FEED ¦ Packing – Batch 2 (100/day) | Packing | 23 | FS | 0 | 19 | FS | 0 | 3 |  | Not Started |  |  |  |  | 2027-04-20 | 2027-04-22 | 2027-04-20 | 2027-04-22 | 3 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-04-22 | 0 | 46499 | 46499
25 | FEED ¦ Dispatch – Vehicles 2-4 (rolling) | Logistics | 24 | SS | 1 | 24 | FF | 1 | 3 |  | Not Started |  |  |  |  | 2027-04-21 | 2027-04-23 | 2027-04-21 | 2027-04-23 | 3 | 0 | Not Started | 0 |  | 0 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-04-23 | 0 | 46500 | 46500
26 | METAL ¦ Finalize manufacturing drawings | Design | [6 empty] | 12 |  | Not Started |  |  |  |  | 2026-10-15 | 2026-10-29 | 2026-10-15 | 2026-10-29 | 12 | 0 | Not Started | 0 |  | 1 | 3 | 0 | 0 | 0 | Not Started | 0% | 2026-10-29 | 0 | 46324 | 46324
27 | METAL ¦ Manufacture all components | Fabrication | 26 | FS | 0 |  |  |  | 45 |  | Not Started |  |  |  |  | 2026-10-30 | 2026-12-25 | 2026-10-30 | 2026-12-25 | 45 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2026-12-25 | 0 | 46381 | 46381
28 | METAL ¦ Powder coating all components | Coating | 27 | FS | 0 |  |  |  | 10 |  | Not Started |  |  |  |  | 2026-12-26 | 2027-01-07 | 2026-12-26 | 2027-01-07 | 10 | 0 | Not Started | 0 |  | 1 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-07 | 0 | 46394 | 46394
29 | METAL ¦ Assembly & packing (75 sets/day) | Assembly | 28 | FS | 0 |  |  |  | 7 |  | Not Started |  |  |  |  | 2027-01-08 | 2027-01-15 | 2027-01-08 | 2027-01-15 | 7 | 0 | Not Started | 0 |  | 2 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-15 | 0 | 46402 | 46402
30 | METAL ¦ Dispatch – 10 vehicles (rolling) | Logistics | 29 | SS | 1 | 29 | FF | 1 | 7 |  | Not Started |  |  |  |  | 2027-01-09 | 2027-01-16 | 2027-01-09 | 2027-01-16 | 7 | 0 | Not Started | 0 |  | 0 | 3 | 1 | 0 | 0 | Not Started | 0% | 2027-01-16 | 0 | 46403 | 46403
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
[28 empty] | 0 | 0 |  |  |  |  | 0 | 0
Formulas:
Planned End = IF(OR([Planned Start]="",NOT(ISNUMBER([Duration (work days)]))),"",WORKDAY.INTL([Planned Start],MAX(1,[Duration (work days)])-1,'Project Info'!$H12,Holidays!$A6:A205))
Forecast / Actual End = IF(OR([Forecast / Actual Start]="",[Forecast / Actual Duration]=""),"",IF(ISNUMBER([Actual End]),[Actual End],WORKDAY.INTL([Forecast / Actual Start],[Forecast / Actual Duration]-1,'Project Info'!$H12,Holidays!$A6:A205)))
End Slip vs Plan (days) = IF(OR(NOT(ISNUMBER([Planned End])),NOT(ISNUMBER([Forecast / Actual End]))),"",IF([Forecast / Actual End]>=[Planned End],NETWORKDAYS.INTL([Planned End],[Forecast / Actual End],'Project Info'!$H12,Holidays!$A6:A205)-1,-(NETWORKDAYS.INTL([Forecast / Actual End],[Planned End],'Project Info'!$H12,Holidays!$A6:A205)-1)))
end if no overshoot = IF(OR([Forecast / Actual Start]="",NOT(ISNUMBER([Duration (work days)]))),"",WORKDAY.INTL([Forecast / Actual Start],MAX(1,[Duration (work days)])-1,'Project Info'!$H12,Holidays!$A6:A205))

## Gantt
GANTT ¦ 1.8M C-Band Antenna System – 500 Sets ¦ <Client name> | [13 empty] | ✔ ON TRACK: forecast finish 23-Apr-2027 meets target 23-Apr-2027
| Week | 0 |  | ◀ pick Day / Week / Month · Scroll = shift timeline by n periods (+ later / − earlier)
LEGEND ▸ bar colour = task status · RED part of a bar = time over the planned duration | [13 empty] | Completed | [7 empty] | In Progress | [7 empty] | Not Started | [7 empty] | On Hold | [7 empty] | Overshoot (over duration) | [7 empty] | Delayed / Affected | [7 empty] | Planned, unused
Orange task name = delayed by predecessor · Red task name = duration overshoot · Pink header = holiday | [13 empty] | Weekly off | [7 empty] | Holiday | [7 empty] | Status date | [7 empty] | ▶ Start | [7 empty] | ↳ Starts after pred. | [7 empty] | ◀ End | [7 empty] | ➜ End feeds others | [7 empty] | ◆ Start = End
2026-10-12 | time axis 2026-10-12 to 2029-01-22
 | time axis 2026-10-18 to 2029-01-28
[14 empty] | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TASK SCHEDULE (Plan vs Forecast / Actual) | [13 empty] | 2026-10-18: Oct 26; 2026-11-08: Nov 26; 2026-12-13: Dec 26; 2027-01-10: Jan 27; 2027-02-07: Feb 27; 2027-03-07: Mar 27; 2027-04-11: Apr 27; 2027-05-09: May 27; 2027-06-13: Jun 27; 2027-07-11: Jul 27; 2027-08-08: Aug 27; 2027-09-12: Sep 27; 2027-10-10: Oct 27; 2027-11-07: Nov 27; 2027-12-12: Dec 27; 2028-01-09: Jan 28; 2028-02-13: Feb 28; 2028-03-12: Mar 28; 2028-04-09: Apr 28; 2028-05-07: May 28; 2028-06-11: Jun 28; 2028-07-09: Jul 28; 2028-08-13: Aug 28; 2028-09-10: Sep 28; 2028-10-08: Oct 28; 2028-11-12: Nov 28; 2028-12-10: Dec 28; 2029-01-07: Jan 29
[14 empty] | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W01 | W02 | W03 | W04
ID | Task | Depends On | Plan Start | Plan End | Fcst / Actual Start | Fcst / Actual End | Status | % Done | Var (days) |  |  |  |  | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 01 | 08 | 15 | 22 | 29 | 05 | 12 | 19 | 26 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 04 | 11 | 18 | 25 | 02 | 09 | 16 | 23 | 30 | 06 | 13 | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22
1 | REFLECTOR ¦ Finalize 1.8M mold design | - | 2026-10-15 | 2026-10-23 | 2026-10-15 | 2026-10-23 | Not Started | 0% | 0 | 3 | 0 | 1 | 46318 | 31 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | REFLECTOR ¦ Mold manufacturing | 1 | 2026-10-24 | 2027-01-19 | 2026-10-24 | 2027-01-19 | Not Started | 0% | 0 | 3 | 1 | 1 | 46406 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | REFLECTOR ¦ Reflector validation | 2 | 2027-01-20 | 2027-01-27 | 2027-01-20 | 2027-01-27 | Not Started | 0% | 0 | 3 | 1 | 1 | 46414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | REFLECTOR ¦ Production (500 nos @ 35/day) | 3 | 2027-01-28 | 2027-02-13 | 2027-01-28 | 2027-02-13 | Not Started | 0% | 0 | 3 | 1 | 1 | 46431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | REFLECTOR ¦ Finishing & packing (35/day) | 4 | 2027-02-15 | 2027-03-03 | 2027-02-15 | 2027-03-03 | Not Started | 0% | 0 | 3 | 1 | 2 | 46449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | REFLECTOR ¦ Dispatch – 8 vehicles (rolling) | 5SS+2, 5FF+1 | 2027-02-17 | 2027-03-04 | 2027-02-17 | 2027-03-04 | Not Started | 0% | 0 | 3 | 1 | 0 | 46450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | FEED ¦ Finalize mold design (6 components) | - | 2026-10-15 | 2026-11-02 | 2026-10-15 | 2026-11-02 | Not Started | 0% | 0 | 3 | 0 | 1 | 46328 | 31 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | FEED ¦ Mold making – Round 1 (Horn, Splitter, Tx Filter) | 7 | 2026-11-03 | 2026-12-11 | 2026-11-03 | 2026-12-11 | Not Started | 0% | 0 | 3 | 1 | 2 | 46367 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | FEED ¦ Mold making – Round 2 (Rx Filter, Tx/Rx OMT) | 8 | 2026-12-12 | 2027-01-16 | 2026-12-12 | 2027-01-16 | Not Started | 0% | 0 | 3 | 1 | 1 | 46403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | FEED ¦ Molding – Round-1 components (1,500 nos) | 8 | 2026-12-12 | 2026-12-16 | 2026-12-12 | 2026-12-16 | Not Started | 0% | 0 | 3 | 1 | 2 | 46372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | FEED ¦ Molding – Round-2 components (1,500 nos) | 9, 10 | 2027-01-18 | 2027-01-21 | 2027-01-18 | 2027-01-21 | Not Started | 0% | 0 | 3 | 1 | 1 | 46408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | FEED ¦ Machining – Round 1, Batch 1 (750 nos) | 10 | 2026-12-17 | 2027-01-04 | 2026-12-17 | 2027-01-04 | Not Started | 0% | 0 | 3 | 1 | 1 | 46391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | FEED ¦ Machining – Round 1, Batch 2 (750 nos) | 12 | 2027-01-05 | 2027-01-21 | 2027-01-05 | 2027-01-21 | Not Started | 0% | 0 | 3 | 1 | 1 | 46408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | FEED ¦ Machining – Round 2, Batch 1 (750 nos) | 11, 13 | 2027-01-22 | 2027-02-08 | 2027-01-22 | 2027-02-08 | Not Started | 0% | 0 | 3 | 1 | 2 | 46426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | FEED ¦ Machining – Round 2, Batch 2 (750 nos) | 14 | 2027-02-09 | 2027-02-25 | 2027-02-09 | 2027-02-25 | Not Started | 0% | 0 | 3 | 1 | 1 | 46443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | FEED ¦ Transport Batch 1 (250 sets) to finishing site | 14 | 2027-02-09 | 2027-02-09 | 2027-02-09 | 2027-02-09 | Not Started | 0% | 0 | 3 | 1 | 1 | 46427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | FEED ¦ Finishing – Batch 1 (1,500 components) | 16 | 2027-02-10 | 2027-03-10 | 2027-02-10 | 2027-03-10 | Not Started | 0% | 0 | 3 | 1 | 2 | 46456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | FEED ¦ Assembly & testing – Batch 1 (250 sets) | 17 | 2027-03-11 | 2027-03-20 | 2027-03-11 | 2027-03-20 | Not Started | 0% | 0 | 3 | 1 | 2 | 46466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | FEED ¦ Packing – Batch 1 (100/day) | 18 | 2027-03-22 | 2027-03-24 | 2027-03-22 | 2027-03-24 | Not Started | 0% | 0 | 3 | 1 | 2 | 46470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | FEED ¦ Dispatch – Vehicle 1 (150 sets) | 19SS+2 | 2027-03-24 | 2027-03-24 | 2027-03-24 | 2027-03-24 | Not Started | 0% | 0 | 3 | 1 | 0 | 46470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | FEED ¦ Transport Batch 2 (250 sets) | 15 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-02-26 | Not Started | 0% | 0 | 3 | 1 | 1 | 46444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | FEED ¦ Finishing – Batch 2 (1,500 components) | 21, 17 | 2027-03-11 | 2027-04-08 | 2027-03-11 | 2027-04-08 | Not Started | 0% | 0 | 3 | 1 | 1 | 46485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | FEED ¦ Assembly & testing – Batch 2 (250 sets) | 22, 18 | 2027-04-09 | 2027-04-19 | 2027-04-09 | 2027-04-19 | Not Started | 0% | 0 | 3 | 1 | 1 | 46496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | FEED ¦ Packing – Batch 2 (100/day) | 23, 19 | 2027-04-20 | 2027-04-22 | 2027-04-20 | 2027-04-22 | Not Started | 0% | 0 | 3 | 1 | 2 | 46499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | FEED ¦ Dispatch – Vehicles 2-4 (rolling) | 24SS+1, 24FF+1 | 2027-04-21 | 2027-04-23 | 2027-04-21 | 2027-04-23 | Not Started | 0% | 0 | 3 | 1 | 0 | 46500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | METAL ¦ Finalize manufacturing drawings | - | 2026-10-15 | 2026-10-29 | 2026-10-15 | 2026-10-29 | Not Started | 0% | 0 | 3 | 0 | 1 | 46324 | 31 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | METAL ¦ Manufacture all components | 26 | 2026-10-30 | 2026-12-25 | 2026-10-30 | 2026-12-25 | Not Started | 0% | 0 | 3 | 1 | 1 | 46381 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | METAL ¦ Powder coating all components | 27 | 2026-12-26 | 2027-01-07 | 2026-12-26 | 2027-01-07 | Not Started | 0% | 0 | 3 | 1 | 1 | 46394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | METAL ¦ Assembly & packing (75 sets/day) | 28 | 2027-01-08 | 2027-01-15 | 2027-01-08 | 2027-01-15 | Not Started | 0% | 0 | 3 | 1 | 2 | 46402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | METAL ¦ Dispatch – 10 vehicles (rolling) | 29SS+1, 29FF+1 | 2027-01-09 | 2027-01-16 | 2027-01-09 | 2027-01-16 | Not Started | 0% | 0 | 3 | 1 | 0 | 46403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Holidays
HOLIDAY LIST
Enter one non-working date per row (yellow cells). Weekly off day(s) are set on the Project Info sheet. Holidays move task dates and are shaded pink on the Gantt chart.
Holiday Date | Holiday Name | Day
2026-10-20 | Dussehra | Tuesday
2026-11-07 | Diwali – day 1 (confirm date) | Saturday
2026-11-09 | Diwali – day 2 (confirm date) | Monday
2026-11-10 | Diwali – day 3 (confirm date) | Tuesday
2026-11-11 | Diwali – day 4 (confirm date) | Wednesday
2027-01-01 | New Year | Friday

## Assumptions
ASSUMPTIONS & BASIS OF DURATIONS
General assumptions
1. Project start = 15-Oct-2026 (date of techno-commercially clear PO + advance), as given.
2. Working calendar: Monday–Saturday, Sunday off (Project Info › Weekly Off). All durations are working days.
3. Holidays: Dussehra 20-Oct-2026; Diwali 4 days (Sat 7, Mon 9, Tue 10, Wed 11 Nov 2026 – Sun 8 Nov is already off; CONFIRM dates); New Year 1-Jan-2027.
4. Quantities: 500 Reflectors, 500 Feed assemblies (3,000 components = 6 per set), 500 Metal Structure sets.
5. Rates (per day): Reflector production 35, finishing & packing 35. Feed: molding 400 (2 machines × 200), machining 50 (2 machines × 25), finishing 60 (2 stations × 30, unchanged from earlier input), assembly & test 30, packing 100. Metal: assembly & packing 75.
6. Vehicles: Reflector 70, Feed 150, Metal 50 per vehicle. Dispatch is rolling – a vehicle leaves when a full load is packed.
7. Reflector finishing starts the working day after production ends (no overlap; ≥12 h cooling gap).
8. Feed: molding & machining at site A; after each 250 sets the lot goes to site B (1 working day transport) for finishing, assembly, testing, packing, dispatch.
9. Feed machining order: round-1 components (both batches) first, then round-2, so machines stay busy while round-2 molds are being made.
10. Link types: FS (finish-to-start), SS+n (starts n days after predecessor starts), FF+n (ends n days after predecessor ends).
11. Target Completion Date is set to the baseline planned finish (23-Apr-2027); overwrite with the contractual date.
12. Status (Report) Date = TODAY(): un-started tasks cannot be forecast to start before today, so unreported progress shows as delay.
13. Owner names, client and project manager are placeholders – edit on Project Info / Tasks.
ID | Task | Days | Basis of duration / link
1 | REFLECTOR ¦ Finalize 1.8M mold design | 7 | Given: 7 days
2 | REFLECTOR ¦ Mold manufacturing | 70 | Given: 70 days
3 | REFLECTOR ¦ Reflector validation | 7 | Given: 7 days
4 | REFLECTOR ¦ Production (500 nos @ 35/day) | 15 | 500 ÷ 35/day = 14.3 → 15 days; starts after validation
5 | REFLECTOR ¦ Finishing & packing (35/day) | 15 | 500 ÷ 35/day = 14.3 → 15 days. No overlap with production; starts next working day = ≥12 h cooling gap
6 | REFLECTOR ¦ Dispatch – 8 vehicles (rolling) | 14 | 70 nos/vehicle → 7×70 + 1×10. First 70 packed after 2 days of finishing (start = finishing start +2); last vehicle leaves 1 day after packing ends (end = finishing end +1). 15−2+1 = 14 days
7 | FEED ¦ Finalize mold design (6 components) | 15 | Given: 15 days (Feed Horn, Splitter, Tx/Rx Filter, Tx/Rx OMT)
8 | FEED ¦ Mold making – Round 1 (Horn, Splitter, Tx Filter) | 30 | Given: 30 days, 3 molds in parallel
9 | FEED ¦ Mold making – Round 2 (Rx Filter, Tx/Rx OMT) | 30 | Given: next 3 molds, 30 days
10 | FEED ¦ Molding – Round-1 components (1,500 nos) | 4 | 3 types × 500 = 1,500 ÷ 400/day (2 machines × 200) = 3.75 → 4 days
11 | FEED ¦ Molding – Round-2 components (1,500 nos) | 4 | 1,500 ÷ 400/day = 3.75 → 4 days; needs round-2 molds and free machines
12 | FEED ¦ Machining – Round 1, Batch 1 (750 nos) | 15 | 250 sets × 3 types = 750 ÷ 50/day (2 machines × 25) = 15 days
13 | FEED ¦ Machining – Round 1, Batch 2 (750 nos) | 15 | 750 ÷ 50/day = 15 days; done before round-2 molds are ready to avoid idle machines
14 | FEED ¦ Machining – Round 2, Batch 1 (750 nos) | 15 | 750 ÷ 50/day = 15 days; completes the 250-set batch 1
15 | FEED ¦ Machining – Round 2, Batch 2 (750 nos) | 15 | 750 ÷ 50/day = 15 days; completes batch 2
16 | FEED ¦ Transport Batch 1 (250 sets) to finishing site | 1 | Assumed 1 day
17 | FEED ¦ Finishing – Batch 1 (1,500 components) | 25 | 1,500 ÷ 60/day (2 stations × 30) = 25 days
18 | FEED ¦ Assembly & testing – Batch 1 (250 sets) | 9 | 250 ÷ 30/day = 8.3 → 9 days
19 | FEED ¦ Packing – Batch 1 (100/day) | 3 | 250 ÷ 100/day = 2.5 → 3 days
20 | FEED ¦ Dispatch – Vehicle 1 (150 sets) | 1 | 150 sets packed after 1.5 days → leaves after 2 packing days (start = packing start +2)
21 | FEED ¦ Transport Batch 2 (250 sets) | 1 | Assumed 1 day
22 | FEED ¦ Finishing – Batch 2 (1,500 components) | 25 | 1,500 ÷ 60/day = 25 days; finishing stations busy with batch 1 first
23 | FEED ¦ Assembly & testing – Batch 2 (250 sets) | 9 | 250 ÷ 30/day = 8.3 → 9 days
24 | FEED ¦ Packing – Batch 2 (100/day) | 3 | 250 ÷ 100/day = 2.5 → 3 days
25 | FEED ¦ Dispatch – Vehicles 2-4 (rolling) | 3 | V2 = 100 left from batch 1 + 50 from batch 2 (ready after 1 packing day), V3 = 150, V4 = last 50; last leaves 1 day after packing ends. Day 2 to day 4 = 3 days
26 | METAL ¦ Finalize manufacturing drawings | 12 | Given: 12 days after PO
27 | METAL ¦ Manufacture all components | 45 | Given: 45 days
28 | METAL ¦ Powder coating all components | 10 | Given: 10 days
29 | METAL ¦ Assembly & packing (75 sets/day) | 7 | 500 ÷ 75/day = 6.7 → 7 days
30 | METAL ¦ Dispatch – 10 vehicles (rolling) | 7 | 50 sets/vehicle → 10 vehicles; first 50 packed after 1 day (start = packing start +1); last leaves 1 day after packing ends. Day 2 to day 8 = 7 days